Three Year Technology Plan
Nortonville Public Library
 FY 2025- FY 2027

Nortonville Public Library
PO Box 179, 407 Main Street
Nortonville, KS 66060
(913) 886-2060
Fax: (913) 886-3070
Email: director@nortonvillelibrary.com
Web: www.nortonvillelibrary.org

Person writing this plan: Greta Funk, Director

Year 1: 2025

Goal 1: Improve internet speed.

Internet speed continuously improves and changes. To provide the best public access experience, we need to have the best speed for the best price.

1. Call Giant Communications about upgrading speed. Feb. 2025.
2. Check with NEKLS about how Meraki equipment may be affected. Feb. 2025.
3. Contact eRate Solutions regarding additional costs and increased speed. Learn about the procedure for seeking approval for eRate and forms to be filed for planned upgrade July 1, 2025. Feb. 2025
4. Submit information to the library board for their approval and submit required paperwork to eRate. Feb. 2025

Goal 2: Replace/upgrade older patron computers
Look at available options for desktop computers. After determining which type(s) to buy for public access, determine cost. March 2025.
2) Purchase 1-2 new or refurbished computers. March 2025.
3) Contact NEKLS and set up time for computers to be linked to the network. March 2025
4) Compare prices and revisit available options. Purchase 1-2 more patron computers and contact NEKLS to have them added to the network. August-September 2025.

Year 2: 2026

Goal 3: Increase accessibility in our technology offerings.

We worked on obtaining grants for accessibility upgrades on our building and materials in 2023, and the next step is to increase the technology resources we have available to our patrons with disabilities.

1. Research the latest technology that improves accessibility: cost, benefits, how many patrons would benefit from the different types. Create a priority list that takes all of those things into account. Jan. 2026
2. Apply for grants/plan fundraising efforts to help cover the costs of a few at the top of the priority list. Feb-March 2026
3. Purchase new technology (quantity depending on funds raised and the technology budget). Aug. 2026
4. Train staff on new technology, share improvements with the community on social media, in newspapers, on our website. Aug.-Sept. 2026.

Year 3: 2027

Goal 4: Look Into Brand New Technology Offerings

Upgrade software/purchase technology for patrons to use for learning, entertainment, and resources, including VR headsets, mobile Hot Spots, or similar, available technology.

1. Look at all options for software and/or equipment, determine cost, determine community/patron need. Jan.-Feb. 2027.
2. Present findings and proposals to the library board, brainstorm ideas for fundraising and community engagement.
3. Purchase products needed. March-April 2027
4. Contact NEKLS regarding assistance with installation when purchases arrive and train staff on new products. April 2027
5. Plan and market events to introduce new technology to patrons and community. May 2027-end of the year.